## Sheet1
Doc Name | GMM Doc Number | Client Doc Number | Discipline | Doc Category | Planned Sub. Date | Actual Sub. Date | Rev
General Arrangement Drawing of VCM Column1 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Engineering | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column2 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Welding | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column3 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Quality | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column4 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | PMO | Issued for Approval | 2024-12-23 05:30 | 2025-01-02 05:30 | 0
General Arrangement Drawing of VCM Column5 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Engineering | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column6 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Welding | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column7 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Quality | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column8 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | PMO | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column9 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Engineering | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column10 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Welding | Issued for Approval | 2024-12-23 05:30 |  | 0
General Arrangement Drawing of VCM Column11 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | Quality | Issued for Approval | 2025-01-23 05:30 |  | 0
General Arrangement Drawing of VCM Column12 | HEV000141-01-01 | DS-TMP-21-04-A2-MS-001 | PMO | Issued for Approval | 2024-12-23 05:30 |  | 0