## Sheet1
Exported data
Date | Vendor | Source | Offer No | Stage | Material | Welding Process | Welder No | Offer By | Contractor Name | SoNo | SubSoNo | Seam No | Fresh/Rework | Thickness(mm) | Total Spots | Ok Spots | Repair | Repair Length | Slag | Poros | Crack | LF | LP | RSR | Total Visual Defects | C/S | U/C | DRS | U/F | Other Visual Defects | Reshoot | FilmWidth | X | FilmLength | Film Quantity | Total Area of Film Sq. Inch | Total Length MM | Repair % | Length %
21-03-2025 | MUNDRA PETROCHEM LIMITED | Ir 192 | 190325009 | AFTER REPAIR | P8 To P8 | SMAW+SAW | W-294,W-217,W-388,W-397,W-266, | PMP | YLE | HEV000137-19~26 | HEV000137-20 | CS101 | AFTER REPAIR | 18 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | X | 30 | 2 | 240 | 0 | 0.00 % | 0.00 %
21-03-2025 | MUNDRA PETROCHEM LIMITED | Ir 192 | 200325018 | AFTER FINAL WELD | P1 To P1 | GTAW+SMAW | W-117,W-387,W-109, | ARJ | ritesh eng | HEV000137-1~6 | HEV000137-6 | JCS101 | AFTER FINAL WELD | 8 | 38 | 30 | 7 | 68 | 1 | 2 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 1 | 0 | 0 | 1 | 114 | X | 570 | 38 | 64980 | 0 | 18.42 % | 0.63 %
21-03-2025 | MUNDRA PETROCHEM LIMITED | Ir 192 | 200325019 | AFTER FINAL WELD | P1 To P1 | SMAW | W-117, | ARJ | ritesh eng | HEV000137-1~6 | HEV000137-6 | JLS101 | AFTER FINAL WELD | 8 | 1 | 0 | 1 | 30 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | X | 7.5 | 1 | 30 | 150 | 100.00 % | 20.00 %
21-03-2025 | MUNDRA PETROCHEM LIMITED | Ir 192 | 200325020 | AFTER FINAL WELD | P1 To P1 | SMAW | W-518,W-117, | ARJ | ritesh eng | HEV000137-1~6 | HEV000137-6 | JLS101A | AFTER FINAL WELD | 8 | 1 | 0 | 1 | 30 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | X | 7.5 | 1 | 30 | 150 | 100.00 % | 20.00 %
21-03-2025 | MUNDRA PETROCHEM LIMITED | Ir 192 | 240325013 | AFTER FINAL WELD | P8 To P8 | GTAW | W-140, | VRJ | Ansh | HEV000137-13~14 | HEV000137-14 | LS203 | AFTER FINAL WELD | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | X | 5 | 1 | 20 | 50 | 0.00 % | 0.00 %
21-03-2025 | LYB-KBR | Ir 192 | 190325015 | AFTER FINAL WELD | P8 To P8 | GTAW+SMAW | W-511,W-510, | PKA | Ayush | EXP000685-2~2 | EXP000685-2 | CS303 | AFTER FINAL WELD | 10 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | X | 30 | 2 | 180 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325001 | AFTER PWHT | P1 To P1 | GTAW | W-463, | ghb | S.K CONTRACTOR | HEV000147-13~13 | HEV000147-13 | CS312 | AFTER PWHT | 7.82 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | X | 15 | 3 | 180 | 83.88 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325002 | AFTER RESHOOT | P1 To P1 | GTAW+SMAW | W-492, | VPP | VYOM | HEV000153-6~6 | HEV000153-6 | CS305 | AFTER RESHOOT | 11.13 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | X | 7.5 | 1 | 22.5 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325005 | AFTER RESHOOT | P1 To P1 | GTAW+SMAW | W-465,W-492, | VPP | VYOM | HEV000153-6~6 | HEV000153-6 | CS307 | AFTER RESHOOT | 11.13 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | X | 7.5 | 1 | 22.5 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325015 | AFTER FINAL WELD | P1 To P1 | SMAW+GTAW | W-336,W-165, | CPB | GMM TEAM | HEV000147-17~17 | HEV000147-17 | CS104 | AFTER FINAL WELD | 16 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | X | 60 | 4 | 720 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325021 | AFTER FINAL WELD | P1 To P1 | GTAW | W-465, | VPP | NAMAN FAB | HEV000153-24~24 | HEV000153-24 | CS308 | AFTER FINAL WELD | 10.15 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | X | 15 | 3 | 180 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325022 | AFTER FINAL WELD | P1 To P1 | GTAW | W-465,W-492, | VPP | NAMAN FAB | HEV000153-24~24 | HEV000153-24 | CS307 | AFTER FINAL WELD | 10.15 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | X | 15 | 3 | 180 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325023 | AFTER FINAL WELD | P1 To P1 | GTAW | W-465, | VPP | NAMAN FAB | HEV000153-24~24 | HEV000153-24 | CS303 | AFTER FINAL WELD | 10.15 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | X | 15 | 3 | 180 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325024 | AFTER FINAL WELD | P1 To P1 | GTAW | W-465, | VPP | NAMAN FAB | HEV000153-24~24 | HEV000153-24 | CS304 | AFTER FINAL WELD | 10.15 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | X | 15 | 3 | 180 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325025 | AFTER FINAL WELD | P1 To P1 | GTAW | W-465, | VPP | NAMAN FAB | HEV000153-24~24 | HEV000153-24 | CS310 | AFTER FINAL WELD | 8.74 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | X | 15 | 3 | 180 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA PETROCHEMICAL LTD | Ir 192 | 200325026 | AFTER FINAL WELD | P1 To P1 | GTAW | W-465, | VPP | NAMAN FAB | HEV000153-24~24 | HEV000153-24 | CS309 | AFTER FINAL WELD | 8.74 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | X | 15 | 3 | 180 | 0 | 0.00 % | 0.00 %
21-03-2025 | HALDIA | Ir 192 | 130325041 | BEFORE WOL | P1 To P1 | SMAW | W-529, | NCP | DATT ENG PRE FAB | HEV000146-2~2 | HEV000146-2 | LS115 | BEFORE WOL | 40 | 6 | 5 | 1 | 15 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | X | 90 | 6 | 2160 | 2000 | 16.67 % | 0.75 %
21-03-2025 | HALDIA | Ir 192 | 130325042 | BEFORE WOL | P1 To P1 | SMAW | W-529, | NCP | DATT ENG PRE FAB | HEV000146-2~2 | HEV000146-2 | LS116 | BEFORE WOL | 40 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 24 | X | 90 | 6 | 2160 | 2000 | 0.00 % | 0.00 %
21-03-2025 | HALDIA | Ir 192 | 190325012 | AFTER REPAIR | P1 To P1 | SMAW | W-514,W-502,W-529, | NCP | DATT ENG PRE FAB | HEV000146-2~2 | HEV000146-2 | LS110 | AFTER REPAIR | 40 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | X | 15 | 1 | 60 | 300 | 100.00 % | 0.00 %