## Sheet1
Exported data
Sales Order No. | Position | Revision | Branch | Customer | Description | Equipment Type | Main Draw Status | Pending Days | Main BOM Status | Pending Days | Engineer | Responsible 3D | Responsible BoM | Responsible Detail D'Man | Drg/BoM Detail Pending | Name Plate | L/D Ration | Shell Thickness | Motor HP | SORF Flange | Lantern Design | SS C-clamp Qty | ERW Pipe For Leg Support | Insulation Thickness(50 MW + 50 Puff) | SS PFA Lined MHC Pad Type - 500NB | Jacketed Tank Thickness - 3bar | So Line | Order Rec | Disc Tech Offer | Pre Eng Approv Date | Order Qty | Allocated Date | Location | Rev0RsEng | Rev0Rs3DEng | Rev0RsEngChr | Rev0RsBom | rev0_NumberOfDays | rev0_drg_status | rev0_ga_issue_date | rev0_ga_bom_pepared_date | rev0_ga_bom_status | rev0_BmNumberOfDays | rev0_ga_TechClrDt | rev0_ga_PlanningReleaseDt | rev0_Drg_SubDate | rev0_CRS_Rec_Date | rev0_CRS_Eng_Reply | rev0_CRS_Sales_Clr | rev0_CustFinalApprDate | rev0_asbuild_drg_recv | rev0_asbuild_drg_sent | rev0_drg_WorkingDays | rev0_BoM_WorkingDays | Rev1RsEng | Rev1Rs3DEng | Rev1RsEngChr | Rev1RsBom | rev1_NumberOfDays | rev1_drg_status | rev1_ga_issue_date | rev1_ga_bom_pepared_date | rev1_ga_bom_status | rev1_BmNumberOfDays | rev1_ga_TechClrDt | rev1_ga_PlanningReleaseDt | rev1_Drg_SubDate | rev1_CRS_Rec_Date | rev1_CRS_Eng_Reply | rev1_CRS_Sales_Clr | rev1_CustFinalApprDate | rev1_asbuild_drg_recv | rev1_asbuild_drg_sent | rev1_drg_WorkingDays | rev1_BoM_WorkingDays | Rev2RsEng | Rev2Rs3DEng | Rev2RsEngChr | Rev2RsBom | rev2_NumberOfDays | rev2_drg_status | rev2_ga_issue_date | rev2_ga_bom_pepared_date | rev2_ga_bom_status | rev2_BmNumberOfDays | rev2_ga_TechClrDt | rev2_ga_PlanningReleaseDt | rev2_Drg_SubDate | rev2_CRS_Rec_Date | rev2_CRS_Eng_Reply | rev2_CRS_Sales_Clr | rev2_CustFinalApprDate | rev2_asbuild_drg_recv | rev2_asbuild_drg_sent | rev2_drg_WorkingDays | rev2_BoM_WorkingDays | Rev3RsEng | Rev3Rs3DEng | Rev3RsEngChr | Rev3RsBom | rev3_NumberOfDays | rev3_drg_status | rev3_ga_issue_date | rev3_ga_bom_pepared_date | rev3_ga_bom_status | rev3_BmNumberOfDays | rev3_ga_TechClrDt | rev3_ga_PlanningReleaseDt | rev3_Drg_SubDate | rev3_CRS_Rec_Date | rev3_CRS_Eng_Reply | rev3_CRS_Sales_Clr | rev3_CustFinalApprDate | rev3_asbuild_drg_recv | rev3_asbuild_drg_sent | rev3_drg_WorkingDays | rev3_BoM_WorkingDays | Rev4RsEng | Rev4Rs3DEng | Rev4RsEngChr | Rev4RsBom | rev4_NumberOfDays | rev4_drg_status | rev4_ga_issue_date | rev4_ga_bom_pepared_date | rev4_ga_bom_status | rev4_BmNumberOfDays | rev4_ga_TechClrDt | rev4_ga_PlanningReleaseDt | rev4_Drg_SubDate | rev4_CRS_Rec_Date | rev4_CRS_Eng_Reply | rev4_CRS_Sales_Clr | rev4_CustFinalApprDate | rev4_asbuild_drg_recv | rev4_asbuild_drg_sent | rev4_drg_WorkingDays | rev4_BoM_WorkingDays | Rev5RsEng | Rev5Rs3DEng | Rev5RsEngChr | Rev5RsBom | rev5_NumberOfDays | rev5_drg_status | rev5_ga_issue_date | rev5_ga_bom_pepared_date | rev5_ga_bom_status | rev5_BmNumberOfDays | rev5_ga_TechClrDt | rev5_ga_PlanningReleaseDt | rev5_Drg_SubDate | rev5_CRS_Rec_Date | rev5_CRS_Eng_Reply | rev5_CRS_Sales_Clr | rev5_CustFinalApprDate | rev5_asbuild_drg_recv | rev5_asbuild_drg_sent | rev5_drg_WorkingDays | rev5_BoM_WorkingDays | Rev6RsEng | Rev6Rs3DEng | Rev6RsEngChr | Rev6RsBom | rev6_NumberOfDays | rev6_drg_status | rev6_ga_issue_date | rev6_ga_bom_pepared_date | rev6_ga_bom_status | rev6_BmNumberOfDays | rev6_ga_TechClrDt | rev6_ga_PlanningReleaseDt | rev6_Drg_SubDate | rev6_CRS_Rec_Date | rev6_CRS_Eng_Reply | rev6_CRS_Sales_Clr | rev6_CustFinalApprDate | rev6_asbuild_drg_recv | rev6_asbuild_drg_sent | rev6_drg_WorkingDays | rev6_BoM_WorkingDays | Rev7RsEng | Rev7Rs3DEng | Rev7RsEngChr | Rev7RsBom | rev7_NumberOfDays | rev7_drg_status | rev7_ga_issue_date | rev7_ga_bom_pepared_date | rev7_ga_bom_status | rev7_BmNumberOfDays | rev7_ga_TechClrDt | rev7_ga_PlanningReleaseDt | rev7_Drg_SubDate | rev7_CRS_Rec_Date | rev7_CRS_Eng_Reply | rev7_CRS_Sales_Clr | rev7_CustFinalApprDate | rev7_asbuild_drg_recv | rev7_asbuild_drg_sent | rev7_drg_WorkingDays | rev7_BoM_WorkingDays | Rev8RsEng | Rev8Rs3DEng | Rev8RsEngChr | Rev8RsBom | rev8_NumberOfDays | rev8_drg_status | rev8_ga_issue_date | rev8_ga_bom_pepared_date | rev8_ga_bom_status | rev8_BmNumberOfDays | rev8_ga_TechClrDt | rev8_ga_PlanningReleaseDt | rev8_Drg_SubDate | rev8_CRS_Rec_Date | rev8_CRS_Eng_Reply | rev8_CRS_Sales_Clr | rev8_CustFinalApprDate | rev8_asbuild_drg_recv | rev8_asbuild_drg_sent | rev8_drg_WorkingDays | rev8_BoM_WorkingDays | Rev9RsEng | Rev9Rs3DEng | Rev9RsEngChr | Rev9RsBom | rev9_NumberOfDays | rev9_drg_status | rev9_ga_issue_date | rev9_ga_bom_pepared_date | rev9_ga_bom_status | rev9_BmNumberOfDays | rev9_ga_TechClrDt | rev9_ga_PlanningReleaseDt | rev9_Drg_SubDate | rev9_CRS_Rec_Date | rev9_CRS_Eng_Reply | rev9_CRS_Sales_Clr | rev9_CustFinalApprDate | rev9_asbuild_drg_recv | rev9_asbuild_drg_sent | rev9_drg_WorkingDays | rev9_BoM_WorkingDays | Rev10RsEng | Rev10Rs3DEng | Rev10RsEngChr | Rev10RsBom | rev10_NumberOfDays | rev10_drg_status | rev10_ga_issue_date | rev10_ga_bom_pepared_date | rev10_ga_bom_status | rev10_BmNumberOfDays | rev10_ga_TechClrDt | rev10_ga_PlanningReleaseDt | rev10_Drg_SubDate | rev10_CRS_Rec_Date | rev10_CRS_Eng_Reply | rev10_CRS_Sales_Clr | rev10_CustFinalApprDate | rev10_asbuild_drg_recv | rev10_asbuild_drg_sent | rev10_drg_WorkingDays | rev10_BoM_WorkingDays | Descrepancie Note
TEST007 | 70 | 0 | Karamsad | MiTuL | TANK,CE02000L,VERT,UNJKTD,GL | TANK | Pending to Send | 18 | BoM Pending(TC Pending) |  | Vijay | Garvit | Dipika | test55 | testing4 | Released | 111 | 222 | 333 | 444 | 555 | 666 | yes test | 666 | 777 | 8899 | TEST007/70 | 01-Apr-2025 | Yes | 01-Apr-2025 | 1 | 10-May-2025 |  | Vijay | Garvit | Vijay | Dipika | 18 | Pending to Send |  |  | BoM Pending(TC Pending) |  |  |  | 01-May-2025 | [6 empty] | 30 | [5 empty] | 0 | Approved | 09-May-2025 |  |  | 3 |  | 06-Apr-2025 |  |  |  |  | 09-May-2025 | [8 empty] | 0 | Approved | 09-May-2025 |  |  | 3 |  | 05-Apr-2025 |  |  |  |  | 09-May-2025 | [36 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900
TEST007 | 60 | 0 | Karamsad | MiTuL | TANK,CE02000L,VERT,UNJKTD,GL | TANK | Pending to Send | 18 | BoM Pending(TC Pending) |  | Vijay | Garvit | Dipika | test3 | testing3 | Pending | 111 | 222 | 333 | 444 | 555 | 666 | yes test | 666 | 777 | 888999 | TEST007/60 | 01-Apr-2025 | Yes | 01-Apr-2025 | 1 | 10-May-2025 |  | Vijay | Garvit | Vijay | Dipika | 18 | Pending to Send |  |  | BoM Pending(TC Pending) |  |  |  | 01-May-2025 | [6 empty] | 30 | [5 empty] | 0 | Approved | 09-May-2025 |  |  | 3 |  | 06-Apr-2025 |  |  |  |  | 09-May-2025 | [8 empty] | 0 | Approved | 09-May-2025 |  |  | 3 |  | 05-Apr-2025 |  |  |  |  | 09-May-2025 | [36 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [9 empty] | testing
TEST007 | 50 | 0 | Karamsad | MiTuL | TANK,CE02000L,VERT,UNJKTD,GL | TANK | Completed | 0 | BoM Pending | 6 |  |  | Khushbu |  |  | Released | [10 empty] | TEST007/50 | 01-Apr-2025 | Yes | 01-Apr-2025 | 1 | [5 empty] | Khushbu | 0 | Approved | 13-May-2025 |  | BoM Pending | 6 | [6 empty] | 13-May-2025 | [8 empty] | 12 | Formal Approval | 02-May-2025 |  | BoM Pending(TC Pending) | 12 |  | 06-Apr-2025 | 02-May-2025 |  |  |  | 08-May-2025 | [8 empty] | 8 | Formal Approval | 06-May-2025 |  | BoM Pending(TC Pending) | 8 |  |  | 06-May-2025 |  |  |  | 09-May-2025 | [8 empty] | 11 | Formal Approval | 03-May-2025 |  | BoM Pending(TC Pending) | 11 |  |  | 03-May-2025 |  |  |  | 02-May-2025 | [8 empty] | 9 | Formal Approval | 05-May-2025 |  | BoM Pending(TC Pending) | 9 |  | 01-Jan-1900 | 05-May-2025 |  |  |  | 04-May-2025 | [8 empty] | 0 | Approved | 07-May-2025 |  | BoM Pending(TC Pending) | 7 |  |  | 07-May-2025 |  |  |  | 07-May-2025 | [8 empty] | 1 | Formal Approval | 08-May-2025 |  | BoM Pending(TC Pending) | 6 |  | 01-Jan-1900 | 11-May-2025 |  |  |  | 11-May-2025 | [8 empty] | 0 | Approved | 08-May-2025 |  | BoM Pending(TC Pending) | 6 | [6 empty] | 02-May-2025 | [8 empty] | 0 | Approved | 07-May-2025 |  | BoM Pending(TC Pending) | 7 |  | 01-Jan-1900 |  |  |  |  | 03-May-2025 | [8 empty] | 0 | Approved | 01-May-2025 |  | BoM Pending(TC Pending) | 13 | [6 empty] | 03-May-2025 | [8 empty] | 0 | Approved | 09-May-2025 |  | BoM Pending(TC Pending) | 5 |  | 01-Jan-1900 |  |  |  |  | 02-May-2025 |  |  |  |  | test
TEST007 | 40 | 0 | Karamsad | MiTuL | TANK,CE02000L,VERT,UNJKTD,GL | TANK | Formal Approval |  | BoM Pending(TC Pending) |  |  |  | Krishna(HO) |  |  | Released | [10 empty] | TEST007/40 | 01-Apr-2025 | Yes | 01-Apr-2025 | 1 | [5 empty] | Krishna(HO) | [42 empty] | 8 | Formal Approval | 06-May-2025 |  | BoM Pending(TC Pending) | 8 |  |  | 06-May-2025 | [40 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [9 empty] | test
TEST007 | 30 | 1 | Karamsad | MiTuL | TANK,CE02000L,VERT,UNJKTD,GL | TANK | Pending to Send | 9 | BoM Pending |  |  |  | Dipika |  |  | Released | [10 empty] | TEST007/30 | 01-Apr-2025 | Yes | 01-Apr-2025 | 1 | 10-May-2025 |  | Vijay | Garvit | Vijay |  | 4 | Pending to Send | [18 empty] | Dipika | 9 |  |  |  | BoM Pending | [65 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [9 empty] | testing
TEST007 | 20 | 0 | Karamsad | MiTuL | TANK,CE02000L,VERT,UNJKTD,GL | TANK | Under Approval | 13 | BoM Pending |  |  |  | Jayesh V |  |  | Released | [10 empty] | TEST007/20 | 01-Apr-2025 | Yes | 01-Apr-2025 | 1 | 08-May-2025 |  |  |  |  | Jayesh V | 13 | Under Approval |  |  | BoM Pending |  |  |  | 06-May-2025 | [6 empty] | 35 | [5 empty] | 0 | Formal Approval | 08-May-2025 |  |  | 4 | [6 empty] | 07-May-2025 | [57 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [9 empty] | testing
TEST007 | 10 | 0 | Karamsad | MiTuL | TANK,CE02000L,VERT,UNJKTD,GL | TANK | Under Approval | 11 | BoM Pending | [6 empty] | Released | [10 empty] | TEST007/10 | 01-Apr-2025 | Yes | 01-Apr-2025 | 1 | 08-May-2025 | [5 empty] | 11 | Under Approval |  |  | BoM Pending | [16 empty] | 0 | Formal Approval | 08-May-2025 |  |  | 4 | [6 empty] | 07-May-2025 | [57 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900 | [41 empty] | 01-Jan-1900