## Order Summary
Order Summary Register
SO Number | Project OTD | PMO Engineer | Customer Name | Equipment Details | Quantities | SO Date | Customer PO | Order Value (INR) | Technical Clearance Date | Commercial Clearance Date | Release Date For Planning | Payment Terms | LD | Potential LD (INR) | Contractual Delivery Date (Original) - CDD | Contractual Delivery Date (Revised) - CDD | Expected Delivery Date | Delivery Terms | Customer Contact Person Detail | Customer | Sales / Application | Engineering | Planning | Procurement | Quality | Manufacturing | Packing | Logistics | EXIM | PMO | CET
SO1234 | Yellow | Nikhil Baridun | Xyz Enterprise | Vessel With Agitator | 22 | 02-Jan-2026 | PO1234 | 2300000 | TC Pending | CC Pending | RP Pending | payment terms | 0.5-5.0 | 11500.00 | 15-01-2026 00:00:00 |  | 17-01-2026 00:00:00 | delivery terms | cust com 1 | need 2 bladesasdasd dassssssssssssss
SO123477 | Red | Setul Majmudar | ABC Enterprise | Agitator | 9 | 01-Jan-2026 | PO123477 | 2678000 | TC Pending | CC Pending | RP Pending | ppp | 0.5-5.0 | 66950.00 | 08-01-2026 00:00:00 |  | 10-02-2026 00:00:00 | ooo | ooo | need 2 extra impeller blades | need 2 blades |  | need 2 extra impeller blades | Panel order need to finalize and drawing to submit for approval_221125 |  |  |  | blades, need 2 blades new
MSE001169 | Yellow | Setul Majmudar | BHANSALI ENGINEERING POLYMERS LTD | Vessel With Agitator | 3 | 24-Dec-2025 | BEPL/PO/CAP/25-26/24 | 17500000 | TC Pending | CC Pending | RP Pending | 10%ADV;15%Raw Mat;65% AD within 7 days;10 %PBG | 0 | 0 | 18-05-2026 00:00:00 |  | 30-06-2026 00:00:00 | Within 5 months post receipt of PO. | 97733 33502 | Approval of the submitted GAD of Reactor and agitator |  |  |  |  | ITP of the Agitator and reactor
EXP000900 | Red | Rushikesh Chavan | Cristalia Chemical Pharmaceutical Ltda | ANFD | 2 | 24-Feb-2026 | 4500127066 | 120135885 | TC Pending | CC Pending | RP Pending | 30% advance along with order Balance against irrevocable confirmed Letter of Credit with any reputed international bank, payable at site |  |  | 08-08-2026 00:00:00 |  | 31-12-2026 00:00:00 | FCA | XXXX@XXX.com | Approval on the proposed system architecture for the control system, Response from Gabriel against queries raised on 25.03.2026 |  | Revised GA Drawing Submission, Raw Material Requirement, Bought out requirement |  | Isolator & PTS - PO Release to DEC, Updated offer from DEC |  |  |  |  | Get the approved datasheet of PSV & Rupture Disc from ESV and share it to engineering, so they can provide technical specification for the inquiry
SO1111 | Yellow | Kirit Vadhiya | PQR LTD | Agitator | 1 | 14-Feb-2026 | PO1111 | 100 | TC Pending | CC Pending | RP Pending | 10% advance. 80% against PI prior to dispatch; 10% against commissioning | 0.5 % TO 5% |  | 14-04-2026 00:00:00 |  | 25-04-2026 00:00:00 | Ex-works | pqr | Advance payment, GA drawing approval |  | GA drawing submission
EXP000852 | Red | Rushikesh Chavan | GMM Pfaudler US Inc. / Biovectra | ANFD | 1 | 18-Aug-2025 | 5768105 | 62642240 | TC Pending | CC Pending | RP Pending | 30% down, balance on shipment |  |  | 18-04-2026 00:00:00 |  |  | DAP | Matthew Roderick - matthew.roderick@pfaudler.com |  |  | Documents to consultant for review |  | Ordering of Sampling Valve (FAMAT)
MSE001177 | Red | Kirit Vadhiya | Greenleaf chemtech | Vessel With Agitator | 2 | 13-Jan-2026 | GLCTPL/PLANT/2025-26/244/01 | 23600000 | TC Pending | CC Pending | RP Pending | 15% Advance, Balance 85% against dispatch of the material within 10 days | 0 | 0 | 10-04-2026 00:00:00 |  |  | FOR site | JIGNESH PATEL | ITP Approval |  | Rector fabrication drawings release by, Internal coil and limpet coil requirement , Magnet used from stock, RM will be release by , Agitator fabrication drawing release by |  | 50 HP motor order placement to Akhsar, Dish end order placed to STAR ENGINEERS expected on
MSE001182 | Yellow | Ishan Jadav | APCOTEX INDUSTRIES LTD | Vessel With Agitator | 2 | 20-Jan-2026 | 3300002414 | 8712000 | TC Pending | CC Pending | RP Pending | 20%ABG,40%Before Dispatch,30%After Dispatch,10%PBG | 0.5 to 5% of PO value |  | 03-06-2026 00:00:00 |  | 30-06-2026 00:00:00 | FOR YOUR WORKS (Dahej) | Smitesh Telavane
MSE001095 | Yellow | Ishan Jadav | VA TECH WABAG LTD | Agitator | 23 | 14-May-2025 | EPC-PO-48996 / 10P179 | 33300000 | TC Pending | CC Pending | RP Pending | 90%Letter of Credit & 10% Commissioning & PBG | 0.5 to 5% of PO value |  | 30-09-2025 00:00:00 |  | 30-06-2026 00:00:00 | FOR YOUR WORKS | Shrikant Karandikar | Update the revised CDD in LN and inform to customer |  |  | Release of Raw material requirement
EXP000901 | Red | Rushikesh Chavan | Cristalia Chemical Pharmaceutical Ltda | ANFD | 1 | 24-Feb-2026 | 4500127064 | 54872026 | TC Pending | CC Pending | RP Pending | 30% advance along with order Balance against irrevocable confirmed Letter of Credit with any reputed international bank, payable at site |  |  | 13-08-2026 00:00:00 |  | 31-12-2026 00:00:00 | FCA | XXXX@XXX.com | Approval on the proposed system architecture for the control system |  | Bought out and Raw Material Requirement, Revised GA Drawing Submission |  | Isolator & PTS - PO Release to DEC
FND000707 | Red | Kirit Vadhiya | Hikal Ltd. | ANFD | 1 | 24-Feb-2026 | 6036405 | 12500000 | TC Pending | CC Pending | RP Pending | 30%ABG,60%Adv. Prior to Dispatch & 10%PBG | 0.5-5 | 437500.00 | 09-06-2026 00:00:00 |  | 03-08-2026 00:00:00 | FOR Site | ashish_gaur@hikal.com |  |  | Power pack drawings submission |  | Bonding plate expected at GMM works | [5 empty] | 28T dish head plate material.
EXP000886 | Yellow | Ishan Jadav | SAFE SULPHUR SYSTEMS LTD | Agitator | 1 | 20-Dec-2025 | SSS-0076-PS-POD-0002 | 11000 | TC Pending | CC Pending | RP Pending | 30%Advance,Balance Against Prior to Dispatch |  |  | 17-03-2026 00:00:00 |  | 31-05-2026 00:00:00 | FCA | PATRICK LUMLEY
111 | Green | Nitin Suthar | sss | ANFD | 1 | 21-Mar-2026 | 111 | 10 | TC Pending | CC Pending | RP Pending | sss | 101 | -22 | 25-03-2026 00:00:00 |  | 09-03-2026 00:00:00 | sss | sss
ENG000138 | Red | Rushikesh Chavan | DR. REDDYS LABORATORIES LTD. | ANFD | 1 | 03-Mar-2026 | 4100135878 | 85000000 | TC Pending | CC Pending | RP Pending | 90% 45 Days,10%Commis/120Days supply with 10% PBG | LD005 |  | 30-08-2026 00:00:00 |  | 30-09-2026 00:00:00 | FOW | kuppukulandayan@drreddys.com | approval on submitted SS316L Reactors and Tanks |  | SS316L Reactors Bought out requirement, Raw material requirement of agitators |  | SS316L Reactors & Tanks Procurement, GMS ordering for SPPS | QAP of SS316L Reactors & Tanks
SO111 | Green | Setul Majmudar | Cust_SSS | Agitator | 50 | 04-Apr-2026 | PO111 | 4390987 | TC Pending | CC Pending | RP Pending | testing | 101 | 0.00 | 08-04-2026 00:00:00 |  | 11-04-2026 00:00:00 | testing | testing
SO222 | Green | Setul Majmudar | Cust_SSS | Agitator | 50 | 04-Apr-2026 | PO222 | 10 | TC Pending | CC Pending | RP Pending | test | 101 | -11 | 08-04-2026 00:00:00 |  | 09-04-2026 00:00:00 | test | test
SO333 | Green | Setul Majmudar | Cust_SSS | ANFD | 50 | 04-Apr-2026 | PO333 | 50000000 | TC Pending | CC Pending | RP Pending | sss | 303 | 0.00 | 07-04-2026 00:00:00 |  | 11-04-2026 00:00:00 | ssss | ssss | sss, tedt
so 555 | Yellow | Setul Majmudar | 555 | Agitator | 2 | 10-Apr-2026 | po 555 | 2678000 | TC Pending | CC Pending | RP Pending | rrr | 0.5-5.0 | 13390.00 | 08-01-2026 00:00:00 |  | 15-01-2026 00:00:00 | rrr | comm1
SO 999 | Yellow | Setul Majmudar | 999 | VCD | 2 | 10-Apr-2026 | PO 999 | 10000 | TC Pending | CC Pending | RP Pending | rrr | 0.5-5 | 100.00 | 11-04-2026 00:00:00 |  | 24-04-2026 00:00:00 | rrr | sss