## Potential LD Summary
Potential LD Summary Register
Customer Name | SO Number | SO Date | PO Number | PO Date | Equipment Type | Cont. Delivery Date(Original) | Revised Delivery Date | Expected Delivery Date | Delay in days | Order Value | LD Clause | LD Applicable (%) | LD Amount
Xyz Enterprise | SO1234 | 02-Jan-2026 | PO1234 | 22-Jan-2026 | Vessel With Agitator | 15-Jan-2026 |  | 17-Jan-2026 | 2 | 2300000 | 0.5-5.0 | 0.5% | 11500.00
ABC Enterprise | SO123477 | 01-Jan-2026 | PO123477 | 07-Jan-2026 | Agitator | 08-Jan-2026 | 08-Jan-2026 | 10-Feb-2026 | 33 | 2678000 | 0.5-5.0 | 2.5% | 66950.00